OE GROUP  ·  TFML + OEA

Phase 1 — Production Build Roadmap

AI-Led · 14-Day Workflow (10-day compression option)

Board Confidential  ·  July 2026

# 1.  Objective

Phase 1 hardens the proven proof-of-concept into a production system for live client use. The POC already delivers all six AURA modules — resident portal, vendor management, service-charge administration, gated vendor payments, immutable audit, and a role-scoped BI dashboard — verified on managed cloud with dual-brand data isolation. Phase 1 does not re-build these; it makes them production-grade: real money movement, self-service onboarding, per-brand channels, richer vendor evaluation, personal reporting, a production UX, offline resilience, and full compliance and security.

Build model: in-house, AI-led end-to-end, mirroring the POC cadence. The plan is 14 days for the comprehensive scope; a 10-day compression (noted at the end) defers offline/PWA and some UX polish to a fast-follow.

# 2.  Guardrails (carried from the POC)

- Human-in-the-loop for money — no vendor payment executes without service verification, performance validation and recorded approvals.

- Row-Level Security is the enforced backstop; UI gating sits on top, never in place of it.

- NDPA (2023) + GDPR alignment; immutable, append-only audit; soft-delete only.

- No live payment credentials until the collection/remittance controls and daily reconciliation pass.

- Evidence over assertion — every day has a verification gate that must pass before the next begins.

# 3.  Phase 1 scope — what we add

Twelve workstreams, drawn from the tracked gaps in the reconciled roadmap:

- Production infrastructure & environment isolation (separate from the POC).

- Four-layer brand isolation — DNS/routing, JWT org-claims, API middleware, on top of DB RLS.

- Self-service onboarding — orgs, staff, vendors, owners and tenants enrol in-app.

- Live collections — Paystack (Naira) + Flutterwave (FX), segregated ledger, receipts.

- Live remittance — Paystack Transfers through the B4 gate; daily bank-vs-ledger reconciliation.

- Per-org inbound channel routing — each brand's WhatsApp/Telegram lands in its own org.

- KPI/SLA-driven, dual-source vendor evaluation — tenant + FM/PM, computed not free-typed.

- Role-appropriate personal reporting — tenant request-tracking, vendor performance & pipeline.

- Production UX pass — mobile navigation, accessibility (WCAG AA), toasts, PDF export.

- Offline PWA — installable, resilient to Nigerian connectivity and power realities.

- Compliance & security hardening — NDPA/GDPR artifacts, rate-limiting, pen & load testing.

- UAT, staff training and go-live.

# 4.  The 14-day workflow

Grouped into three tracks. Each day is a self-contained deliverable behind a verification gate.

## Track A — Infrastructure, isolation & onboarding (Days 1–4)

| Day | Focus | Key tasks | Done when |
| --- | --- | --- | --- |
| 1 | Production environment & DevSecOps | - Dedicated production Supabase project (isolated from POC data) + production Vercel project - Secrets in a managed vault (Infisical); activate webhook auth (WhatsApp app secret + Telegram secret token) - Error tracking (Sentry), uptime monitoring, automated backups | Production is a clean, isolated, monitored environment; no POC data shared. |
| 2 | Four-layer brand isolation | - DNS/domain routing (tfmconsultant.com / oraegbunike.com); JWT org-claims; brand API middleware - Automated cross-brand access test as a repeatable artifact | Cross-brand test passes at all four layers; a TFML user cannot reach OEA data by any route. |
| 3 | Org & member onboarding | - Org creation/nesting (parent_org_id, delivery_brand); admin ‘add member’ + role assignment UI - Invite-by-email flow; onboarding actions audited | An admin onboards a new org and enrols a member end-to-end. |
| 4 | Vendor & tenant self-service | - Vendor self-registration with admin approval; tenant↔unit assignment; property/unit management UI | A vendor self-registers (pending approval); a tenant is linked to a unit and sees their statement. |

## Track B — Money, channels & evaluation (Days 5–9)

| Day | Focus | Key tasks | Done when |
| --- | --- | --- | --- |
| 5 | Live collections | - Paystack (Naira) + Flutterwave (FX) checkout for SC invoices; HMAC-verified webhooks - In-app segregated ledger; branded receipts | A test-mode collection posts, updates the ledger, and reconciles. |
| 6 | Live remittance & funds control | - Paystack Transfers for payouts through the existing B4 gate; segregated client-funds ledger - Daily bank-vs-ledger reconciliation job | A gated test-mode transfer executes; daily reconciliation passes; no transfer without approvals. |
| 7 | Per-org inbound channel routing | - Map inbound number/bot → org (or per-org numbers/bots); remove the POC single-org hardcoding | A message to the TFML channel creates a TFML-org ticket; OEA is separate. |
| 8 | KPI/SLA evaluation foundation | - Admin-editable rubric (criteria, points, SLA targets, effective-dating); ‘completed’ job status + completed_at - Auto-measurement of response/completion time vs SLA from timestamps | Admin edits the rubric; response/completion auto-computed, not typed. |
| 9 | Dual-source vendor scoring | - Tenant satisfaction review on completion + FM/PM operational checklist, combined via AURA weights - Vendor sees the feedback that fed the score | A tenant review + FM eval combine into the composite; no free-typed scores remain. |

## Track C — Reporting, experience, compliance & go-live (Days 10–14)

| Day | Focus | Key tasks | Done when |
| --- | --- | --- | --- |
| 10 | Role-appropriate reporting | - Tenant ‘Track my request’ status timeline + SC/payment history + notifications feed - Vendor ‘performance & pipeline’ — score trend, job kanban, pay status, percentile band | A tenant tracks a request end-to-end; a vendor sees their trend + pipeline. |
| 11 | Production UX pass + PDF | - Mobile drawer nav, password reveal, toasts, loading skeletons, empty states, confirmation dialogs - WCAG AA accessibility; branded PDF export (statements, remittance advice) via @react-pdf/renderer | Accessibility + mobile audits pass; PDFs generate correctly. |
| 12 | Offline PWA | - Service worker, manifest, offline caching of key views, background sync for queued requests, web push | The portal is installable and usable offline; a request queued offline syncs on reconnect. |
| 13 | Compliance & security hardening | - NDPA/GDPR: DPO designation, DPAs with processors, privacy policy, consent, data-retention audit - Webhook rate-limiting (Upstash); automated pen test (OWASP ZAP); load test (k6) to target | No critical findings; load target met; compliance artifacts in place. |
| 14 | UAT, training & go-live | - Multi-role UAT script; staff training (TFML + OEA); user guides; production data migration - Final go/no-go; production deploy; rollback plan confirmed | UAT sign-off across all roles; system live; rollback confirmed. |

# 5.  Deliverables

- A production deployment on isolated, monitored managed cloud with activated webhook authentication.

- Live, reconciled collections and gated remittance in the payment provider's test/live mode.

- Self-service onboarding for every role; per-brand channel routing; four-layer brand isolation with a passing cross-brand test.

- KPI/SLA-driven, dual-source vendor evaluation and role-appropriate tenant/vendor reporting.

- A production-grade, accessible, offline-capable UX with branded PDF outputs.

- Compliance pack (DPO, DPAs, privacy, retention) and security evidence (pen test, load test).

- UAT sign-off, staff training materials and user guides.

# 6.  Risks & mitigations

| Risk | Mitigation |
| --- | --- |
| Payment provider onboarding/KYC delays (Paystack/Flutterwave, bank account) | Start provider verification on Day 1 in parallel; build against test mode; go live the moment KYC clears. |
| WhatsApp Business verification & number health | Complete Meta business verification early; keep Telegram + SMS fallback proven as the B8 cascade. |
| Live money movement risk | Human-in-the-loop gate retained; segregated ledger; daily reconciliation; no keys until controls pass. |
| Compressed timeline vs scope | 10-day compression defers PWA (Day 12) and some UX polish (Day 11) to a fast-follow, without touching money or isolation. |
| Data migration from POC | POC uses synthetic data; production starts clean with real onboarding — no risky migration of demo records. |

# 7.  Exit gate — go-live criteria

- Cross-brand isolation test passes at all four layers.

- A collection and a gated remittance both reconcile in the provider environment.

- Every role can be onboarded in-app and sees only its own correctly-scoped data.

- No critical security findings; load target met; NDPA/GDPR artifacts signed off.

- Multi-role UAT completed clean; rollback plan confirmed.

Compression to 10 days: keep Days 1–10 and Days 13–14; fold Day 11 (UX polish) into a post-launch sprint and defer Day 12 (PWA) to a fast-follow. Money movement, brand isolation, onboarding, evaluation and compliance all remain in scope — only offline resilience and cosmetic polish move out.

Companion documents (in the repository): RECONCILED_ROADMAP.md, PHASE1_VENDOR_EVALUATION.md, SECURITY_REVIEW.md, UX_BACKLOG.md, DEPLOYMENT.md.