## Slide 1
BOARD CONFIDENTIAL
TENTai is live
Going live: where we are
Both payment providers have approved OEA. Staff training is under way. A new Executive role is ready for Engr Ola.
7 October 2026
Prepared for the Board · OE Group of Companies (TFML · OEA)
Notes: This edition replaces the 29 Sept one. It is written for the board in plain language. Sources: the go-live tracker, the Memorandum to the Chairman of 6 Oct 2026, and the project lead's update of 7 Oct (gateway approvals, training, Executive role).

## Slide 2
Where we are today
Four things to know this morning.
Live and in use
The system went live on 28 September. OEA is loading its properties and its staff.
Payments approved
Paystack and Flutterwave have both approved OEA's business verification.
Training under way
A three-day staff programme began yesterday, starting with the property managers.
Executive role ready
Engr Ola's new role is built into the system. It has not been tested yet.
OE Group · TENTai · Board Confidential · 7 October 2026
Notes: Live since 28 Sept (board GO). Gateway approvals and training: project lead's update, 7 Oct. Executive role: built 2-3 Oct (migrations 0306-0312), merged and deployed 3 Oct; not yet tested with the person who will hold it.

## Slide 3
The road so far
From switching on to everyday use, in seven steps.
24 Sep
Switched on
The live system was set up, empty and secure
26–27 Sep
Safety-tested
Security, heavy-load and backup tests all passed
28 Sep
Board said GO
OEA began loading its properties and staff
2–3 Oct
New features
Executive role and two-step sign-in added
Early Oct
Payments approved
Paystack and Flutterwave approved OEA
6–8 Oct
Staff training
Three days of hands-on training
Next
First real payment
Checked by hand, end to end
OE Group · TENTai · Board Confidential · 7 October 2026
Notes: Tracker dates: production deployed 24 Sept (5.2); self-assessment and load tests 26-27 Sept (6.1); board GO 28 Sept (6.4); Executive role and two-step sign-in merged 3 Oct. The date of the gateway approvals is per the project lead's report; 'Next' is tracker item 6.6, not yet done.

## Slide 4
Payments: both providers have said yes
OEA's business verification is approved by Paystack and by Flutterwave.
Paystack
APPROVED
Can send automatic payouts to vendors and landlords
Flutterwave
APPROVED
Collects tenant payments, in Naira and foreign currency
What happens next
1
Connect the live keys
An administrator adds OEA's live keys for both providers in the system's banking settings.
2
Make one small real payment
Check by hand that it lands in OEA's own account and shows correctly.
3
Open online payment to tenants
Tenants can then pay by card or bank online, and get a receipt at once.
Until the keys are connected, tenants pay by bank transfer and upload proof. Three people check each one before it counts, and vendors are paid by recorded bank transfer.
OE Group · TENTai · Board Confidential · 7 October 2026
Notes: Both approvals are per the project lead's update of 7 Oct. How the system uses them, as built (decision 4 amendment, PR #53): Flutterwave is preferred for collecting Naira and foreign-currency payments; payouts use Paystack only. With both keys connected, collections go through Flutterwave and automatic payouts through Paystack. The board minute drafted on 23 Sept (Flutterwave replacing Paystack) should now record both. Connecting keys is tracker 3.5 and 5.5a; the first real payment is 6.6.

## Slide 5
Staff training: three days, under way
Hands-on sessions so every desk can use the system from day one.
DAY 1
Tue 6 Oct
HELD
Property managers
The staff on the ground, who log and follow up every request
DAY 2
Wed 7 Oct
TODAY
Other staff groups
Scheduled for today
DAY 3
Thu 8 Oct
TOMORROW
Other staff groups
Scheduled for tomorrow
Cost: staff training (₦250,000) is one of the items still owed in the Stage 2 funding.
OE Group · TENTai · Board Confidential · 7 October 2026
Notes: Per the project lead, 7 Oct: the three-day programme began yesterday (6 Oct) for property managers (staff on ground); the other sessions are today and tomorrow. Which groups attend days 2 and 3 should be named on the slide if known. The ₦250,000 is from section 2 of the Memorandum to the Chairman (6 Oct).

## Slide 6
A new role for Engr Ola: Executive
Built into the system for OEA, one level below the Managing Partner.
Built
Added to the system on 2–3 October
Onboarding
Instruction given to bring her onto the system
Testing
Not yet tested with her. Next, once she is set up
What she will be able to do
See all of OEA's day-to-day operations, across every property
Raise, assign and close work, as a property or facilities manager does
Invite facilities managers, property managers and operations staff
Approve operations requests for money up to ₦500,000, never her own
She does not release money. Paying out stays with the Payment Officer.
OE Group · TENTai · Board Confidential · 7 October 2026
Notes: Decision 59 (operations_executive, migrations 0306-0312): OEA only; rank above the regional manager, below the MP. Organisation-wide operations (0309); may approve stage 2 of an ops requisition at or below the operator-set limit, ₦500,000 by default, never one she raised; no money release, ledger, export or audit. Several powers are operator switches (0310-0312). Untested with the real account; a demo login exists on staging (oea.opsexec@oegroup.test).

## Slide 7
Stage 2 funding: half released
From the Memorandum to the Chairman, 6 October 2026.
₦1,066,359.38
Stage 2 approved
₦533,000
Released so far
₦533,359.38
Still to be released
Stage 2 released
50% released
The whole Phase 1 budget is ₦5,257,421.88. With this part release, ₦4,724,062.50 has been released in total, about 90%.
OE Group · TENTai · Board Confidential · 7 October 2026
Notes: Memo section 2: approved Phase 1 ₦5,257,421.88; released before Stage 2 ₦4,191,062.50; Stage 2 ₦1,066,359.38, part released ₦533,000, balance ₦533,359.38. The total released (₦4,724,062.50 = 4,191,062.50 + 533,000; 89.9%) is derived here, not stated in the memo.

## Slide 8
How the ₦533,000 was spent
Testing, and the subscriptions that keep the system running.
Chart: 
| Website hosting (Vercel) | AI backup service (Google) | New live database | WhatsApp business line (360dialog) | Security and heavy-load testing
₦ | 28000 | 43000 | 64358 | 156800 | 247000
TOTAL SPENT
₦541,800
₦8,800 more than released. The extra comes from the contingency reserve.
WhatsApp lapsed
The WhatsApp subscription expired on 1 October and was cancelled. It could not be paid out of pocket.
OE Group · TENTai · Board Confidential · 7 October 2026
Notes: Memo section 2 expenditure, as stated: new blank database 64,358; deployment manager 28,000; penetration and load test 247,000; 360dialog WABA 156,800; AI fallback (Google API) 43,000; total stated 541,800; balance -8,800. CHECK BEFORE PRESENTING: the five lines add to ₦539,158, not ₦541,800 (a ₦2,642 difference). Section 3: the WABA subscription expired 1 Oct and was cancelled; confirm whether WhatsApp is back on before presenting.

## Slide 9
What is still owed
Two items remain from the Stage 2 budget.
₦250,000
Staff training
The three-day programme under way this week.
₦406,359.38
Contingency reserve (15%)
₦193,158 of it has already gone on keeping subscriptions running, so work did not stall.
TOTAL OWED
₦665,159.38
Includes the ₦8,800 overspend. The contingency absorbs it, so the balance to release stays ₦533,359.38.
OE Group · TENTai · Board Confidential · 7 October 2026
Notes: Memo section 2 'Still owed': staff training 250,000; contingency reserve (15%) 406,359.38; total owed 665,159.38 (= 656,359.38 + the 8,800 overspend). Section 3: ₦193,158 of the contingency already spent on platform subscriptions. CHECK: the two starred subscription lines (database 64,358 + WABA 156,800) add to ₦221,158, not ₦193,158.

## Slide 10
What it costs to keep running
Monthly subscriptions after go-live, from the 6 October memo.
WHAT
PER MONTH
PER YEAR
Database
Supabase
₦75,124
₦901,488
Hosting
Vercel
₦49,322
₦591,864
WhatsApp
WhatsApp Business (OEA)
₦79,187.50
₦950,250
AI
Claude, with Gemini backup
₦170,000
₦170,000
Monitoring
Sentry, Better Uptime (optional)
₦48,450
₦588,000
Total
₦422,083.50
₦3,201,602
Already covered or free
Website names
Paid for two years
Paystack, Flutterwave
Fees per payment only
Form protection, Telegram
Free for now
Data backups
On TFML's Google Workspace
OE Group · TENTai · Board Confidential · 7 October 2026
Notes: Memo section 4, figures exactly as stated. CHECK BEFORE PRESENTING: two rows do not follow month x 12. AI shows ₦170,000 a month and ₦170,000 a year; Monitoring shows ₦48,450 a month (x12 = ₦581,400) and ₦588,000 a year. ₦422,083.50 a month x 12 would be ₦5,065,002 a year, against the ₦3,201,602 stated. Replaces the 3 Sept table (₦516,375 a month).

## Slide 11
Still to finish
What remains before the system is complete and fully compliant.
Connect live payment keys
Then one real payment, checked by hand
NEXT
Onboard and test Engr Ola's role
Instruction given; testing follows
NEXT
Finish staff training
Days 2 and 3: today and tomorrow
THIS WEEK
Sign the data agreements
With each outside service provider
OPEN
Legal review of the privacy notice
The notice is published; review owed
OPEN
Register with the NDPC
The national data protection regulator
OPEN
OE Group · TENTai · Board Confidential · 7 October 2026
Notes: Tracker: 3.5/5.5a and 6.6 (keys and first real payment); decision 59 (Executive role); 1.1 processor agreements (none signed as of 28 Sept); 1.2 privacy notice (published 24 Sept, legal review owed); 1.5 NDPC registration. Special-category data (1.6) is also still undecided.

## Slide 12
What we ask the board today
1
Release the Stage 2 balance
₦533,359.38, to finish training and close out Stage 2.
2
Approve the monthly subscriptions
About ₦422,000 a month, so no service is cut off. WhatsApp has already lapsed once.
3
Agree how the two payment providers are used
Flutterwave to collect payments, Paystack to pay vendors and landlords.
4
Support Engr Ola's onboarding this week
So her new role can be tested with her before it is relied on.
LIVE
since 28 September
2 of 2
payment providers approved
3 days
of staff training
OE Group · TENTai · Board Confidential · 7 October 2026
Notes: 1-2 are the memo's recommendation (section 5). 3 replaces the 23 Sept draft minute (Flutterwave instead of Paystack): with both approved, the minute should record both, as the system already uses them. 4 per the project lead's update.