## Slide 1
BOARD CONFIDENTIAL
OE Group
Phase 1 Progress
Production build of the unified property & facilities platform for TFML and OEA
5 August 2026
Through Day 11 complete · Day 12 (security, compliance & go-live) in progress
Notes: OE Group Phase 1 progress report for the board. As of 5 August 2026 the build is complete through Day 11 (OEA lettings, analytics console, vendor KPI/SLA evaluation), with Day 12 (security, compliance, UAT, go-live) in progress — started 4 Aug per GO_LIVE_CHECKLIST.md, not yet executed. Verified from BUILD_JOURNAL.md and PHASE1_WORKPLAN.md day-status notes.

## Slide 2
The Phase 1 roadmap at a glance
Foundation, money, lettings, intelligence and launch. Where the build actually is today.
0
Preconditions — accounts, keys, environments
DONE
1
Environment split — demo frozen, Phase 1 on its own database
DONE
2
Brand isolation — each brand walled off, in and at rest
DONE
3
Omnichannel intake + AI triage, notification centre
DONE
★
Foundation build — new UI, branding, asset register, vendor applications
DONE
4
Segregated client-funds ledger + reconciliation
DONE
5
Live collections — checkout to receipt to ledger
DONE
6
Live remittance — vendor payouts + landlord rent, gated
DONE
6.5
Operator-governed permission matrix
DONE
6.75
Property & unit enrolment (create/manage portfolio)
DONE
7
OEA tenant application + KYC intake
DONE
8
Two-tier human review + approval
DONE
9
Lease administration + rent roll
DONE
10
Interactive analytics dashboard
DONE
11
Vendor KPI/SLA evaluation, work-order media, UX pass
DONE
12
Security audit, NDPA pack, UAT, go-live
IN PROGRESS
Notes: The full roadmap. Fifteen of sixteen stages complete: Days 0–6, the inserted foundation build, 6.5, 6.75, and now 7–11 (OEA lettings, analytics console, vendor evaluation). Only Day 12 (security, compliance, UAT, go-live) remains, in progress since 4 Aug.

## Slide 3
A
OE GROUP · USER JOURNEY · LANE A
built · live now
upcoming
ADMIN
Onboard people, set controls, oversee everything, sign off large payments.
1
+
Invite & onboard
staff · vendors · tenants → role
2
Configure controls
threshold · permissions · brand
3
Oversee all tickets & money
🖥 org-scoped dashboard
4
💧 Approve high-value pay
above threshold · gated
5
Analytics console
filters, trends, exports
6
Go-live governance
upcoming · Stage 12
INTAKE
TRIAGE
DISPATCH
WORK
VERIFY
EVALUATE
INVOICE
APPROVE
PAY/REMIT
RECONCILE
REPORT
Notes: Admin lane: invite and onboard, configure controls, oversee all tickets and money, approve high-value payments (gated), analytics console (shipped Day 10). One upcoming ghost remains: go-live governance (Day 12, in progress).

## Slide 4
B
OE GROUP · USER JOURNEY · LANE B
FM / PM
Run assigned properties: dispatch, verify work, manage units & assets.
1
My properties only
property-scoped requests
2
Dispatch
assign vendor to ticket
3
💧 Verify service delivered
gate step ①
4
Manage register
property · unit · asset
5
✓
Review tenant application
property-scoped queue
6
Rent-roll & lease oversight
landlord-ready roll
INTAKE
TRIAGE
DISPATCH
WORK
VERIFY
EVALUATE
INVOICE
APPROVE
PAY/REMIT
RECONCILE
REPORT
built · live now
upcoming
Notes: FM/PM lane: see only my properties, dispatch, verify service delivered (gated), manage register, review tenant application (Day 8), rent-roll and lease oversight (Day 9). No upcoming ghosts remain in this lane.

## Slide 5
C
OE GROUP · USER JOURNEY · LANE C
VENDOR
Fulfil assigned work orders and get paid for completed jobs.
1
Assigned work orders
jobs dispatched to me
2
✓
✕
Accept / decline
respond to dispatch
3
✓
Mark complete
update ticket status
4
$
💧 Submit invoice
gate step ②
5
Payment history
every invoice, always
6
%
Service catalog & pricing
future · unscoped
INTAKE
TRIAGE
DISPATCH
WORK
VERIFY
EVALUATE
INVOICE
APPROVE
PAY/REMIT
RECONCILE
REPORT
built · live now
upcoming
Notes: Vendor lane: assigned work orders, accept/decline, mark complete, submit invoice (gated), payment history (the my-work page’s Payment status table, Day 10). One upcoming ghost remains: service catalog and pricing.

## Slide 6
D
OE GROUP · USER JOURNEY · LANE D
TENANT / RESIDENT
Report an issue, track it, pay charges — from their phone.
1
Report an issue
📱 ✈ 🖥 WhatsApp · Telegram · web
2
AI triage
category + priority
3
Ticket + acknowledgement
"check status" · "it's urgent"
4
Track the request
live status updates
5
Pay service charge
🖥 Paystack → receipt
6
View statements
payment history
7
Apply for tenancy + KYC
on their phone, OEA
8
Pay rent / lease online
upcoming · Stage 9
9
"Track my request" timeline
raised → resolved
INTAKE
TRIAGE
DISPATCH
WORK
VERIFY
EVALUATE
INVOICE
APPROVE
PAY/REMIT
RECONCILE
REPORT
built · live now
upcoming
Notes: Tenant lane: report an issue, AI triage, ticket + ack, track request, pay service charge, view statements, apply for tenancy + KYC (Day 7), “Track my request” timeline (Day 10). One upcoming ghost remains: pay rent / lease online — the ledger side is built (Day 9) but no tenant-facing checkout page was found yet.

## Slide 7
E
OE GROUP · USER JOURNEY · LANE E
OWNER/LANDLORD
Track portfolio health, get paid, sign off on major spend.
1
Portfolio dashboard
performance at a glance
2
Financial reports
statements & P&L
3
$
💧 Receive remittance
gate step ③ · payout
4
✓
Approve major spend
sign off on expenditure
5
Market comps
future · unscoped
6
E-sign documents
future · unscoped
INTAKE
TRIAGE
DISPATCH
WORK
VERIFY
EVALUATE
INVOICE
APPROVE
PAY/REMIT
RECONCILE
REPORT
built · live now
upcoming
Notes: Owner lane: portfolio dashboard, financial reports, receive remittance (gated), approve major spend. Two upcoming ghosts: market comps, e-sign documents.

## Slide 8
F
OE GROUP · USER JOURNEY · LANE F
FINANCE LEAD
Reconcile the ledger, batch-approve payouts, close the books.
1
=
Reconcile ledger
match payments to tickets
2
✓
Batch-approve payouts
vendor invoices, in bulk
3
$
💧 Remit to owners
gate step ④ · payout run
4
Generate reports
org-wide P&L & statements
5
Tax & compliance filing
future · unscoped
6
Multi-entity consolidation
future · unscoped
INTAKE
TRIAGE
DISPATCH
WORK
VERIFY
EVALUATE
INVOICE
APPROVE
PAY/REMIT
RECONCILE
REPORT
built · live now
upcoming
Notes: Finance Lead lane: reconcile ledger, batch-approve payouts, remit to owners (gated), generate reports. Two upcoming ghosts: tax and compliance filing, multi-entity consolidation.

## Slide 9
G
OE GROUP · USER JOURNEY · LANE G
APPROVER
Final sign-off on the largest payments before they release.
1
Review flagged transactions
high-value queue
2
Check supporting docs
invoices, photos, receipts
3
💧 Approve / reject release
gate step ⑤ · final say
4
Approval audit trail
who approved what, when
5
Delegate approval authority
future · unscoped
6
Set approval policy & rules
future · unscoped
INTAKE
TRIAGE
DISPATCH
WORK
VERIFY
EVALUATE
INVOICE
APPROVE
PAY/REMIT
RECONCILE
REPORT
built · live now
upcoming
Notes: Approver lane: review flagged transactions, check supporting docs, approve/reject release (gated final say), approval audit trail. Two upcoming ghosts: delegate approval authority, set approval policy and rules.

## Slide 10
FOUNDATION
Day 0
Preconditions in place
COMPLETE
What was delivered
Set up the workshop before any building began.
A separate development database, isolated from the live demo.
Live error monitoring and uptime watching switched on.
Payment gateway test keys obtained so money paths could be built safely.
THE REAL DEMONSTRATION
Every account, key and environment needed for the build was confirmed in hand — a dedicated development Supabase database, Upstash rate-limiting, Sentry error tracking, an isolated Vercel project, and Paystack test keys — with nothing yet touching real money or the live demo.
Notes: Day 0 gate evidence from the Status board: dev Supabase, Upstash, Sentry, Vercel dev project, Paystack test keys. This stage is about readiness, not visible features.

## Slide 11
TRACK A · FOUNDATION
Day 1
A world that cannot touch the demo
COMPLETE
What was delivered
A fresh Phase 1 workspace running on its own database.
The existing live demo left completely frozen and untouched.
Automatic protection against message floods on both intake channels.
Error reporting proven to be live and delivering.
THE REAL DEMONSTRATION
The live demo and the new Phase 1 environment were shown running side by side — same app, different data — with the demo database provably unchanged. Rate-limiting blocked a flood on the sixth message; a test error arrived in monitoring within seconds.
Notes: Day 1 gate: seeding dev left demo untouched; limiter + Sentry proven live. Build journal confirms demo 26 tickets vs dev 22 on separate hosts.

## Slide 12
TRACK A · FOUNDATION
Day 2
Each brand walled off from the other
COMPLETE
What was delivered
TFML and OEA fully separated — on the way in, not just at rest.
Each brand's WhatsApp / Telegram number routes into its own account.
Four independent layers of isolation, each checked automatically.
The old shared hard-coded organisation removed entirely.
THE REAL DEMONSTRATION
A message sent to TFML's number appeared only under TFML; a message to OEA's number only under OEA — and neither brand could see a trace of the other. The separation held at all four layers under an automated isolation test.
Notes: Day 2 gate: verify-channel-routing, verify-jwt-claims. Kills hardcoded DEMO_ORG_ID; isolation proven at all four layers.

## Slide 13
TRACK A · FOUNDATION
Day 3
Requests in, from anywhere
COMPLETE
What was delivered
Residents can reach the platform by WhatsApp, Telegram or the portal.
AI reads each message, decides what it is and how urgent, and files it.
A personal notification inbox for every user, with channel preferences.
People can enrol their own colleagues by email invitation — no scripts.
THE REAL DEMONSTRATION
A message on any channel became a correctly-categorised ticket automatically, the right person was notified, and an emailed invitation carried a new user through sign-up into exactly the role and organisation they were granted — and nothing more.
Notes: Day 3 gate: verify-notifications, verify-cascade, verify-email-routing. Also invitation acceptance verified in-browser.

## Slide 14
INSERTED SCOPE
★
The platform gets its face and its assets
COMPLETE
What was delivered
Every screen restyled onto one modern, mobile-ready design system.
Each brand controls its own colours, logo, portal name and contacts — no code.
A complete asset register: property, equipment, compliance, custom fields, bulk import.
A public vendor application form with layered anti-abuse controls.
THE REAL DEMONSTRATION
Each brand's portal rendered in its own identity (TFML navy, OEA red) from admin settings alone; an asset import accepted valid rows and refused the bad ones with reasons; a vendor could apply publicly but became payable only after a human approved.
TFML (navy) and OEA (red) portals — separate requests, separate branding, one shared backend.
Notes: Inserted-scope gate: verify-org-theming, verify-asset-access, verify-asset-import, verify-vendor-applications, verify-invitations. This work was added between Days 3 and 4 after a scope check found asset management missing from Phase 1. TFML + OEA portal screenshots embedded (assets/01-portal-tfml.png, assets/02-portal-oea.png) — the paired shot is the visual proof of per-brand isolation.

## Slide 15
TRACK B · MONEY
Day 4
Client money gets a real ledger
COMPLETE
What was delivered
A segregated, double-entry ledger for client funds.
Four safety rules enforced by the database itself, not just the app.
A daily bank-versus-ledger reconciliation that flags any variance.
Balances, journal and reconciliation screens to see it all.
THE REAL DEMONSTRATION
A clean bank statement reconciled to exactly zero variance. A hidden ₦75,000 debit was then deliberately planted — and the system flagged it, reported the line unmatched, and kept both runs on record. The gate that unlocks live payment keys.
The segregated client-funds ledger: money held covers everything owed, per client account.
Notes: Day 4 gate verbatim: clean statement reconciles to 0, planted 75,000 debit flagged. 39 checks across ledger + reconciliation. Client-funds ledger screenshot embedded (assets/03-ledger.png): ₦5,585,000 held / ₦5,460,000 owed / ₦125,000 unallocated.

## Slide 16
TRACK B · MONEY
Day 5
Money coming in, end to end
COMPLETE
What was delivered
Rent and service-charge payments taken through Paystack and Flutterwave.
Every payment verified server-to-server, then posted to the ledger once.
Branded receipts generated on demand, always matching the ledger.
A real test-mode payment recorded live against the true gateway.
THE REAL DEMONSTRATION
A test payment flowed from checkout to receipt to ledger. A forged webhook claiming ₦999,999,999 against a ₦400,000 invoice was ignored — only the ₦250,000 actually presented posted. A live Paystack test then recorded ₦287,000 against a ₦285,000 invoice and correctly flagged the mismatch.
Notes: Day 5 gate: verify-collections, verify-checkout-e2e — payload claiming 999,999,999 ignored, exactly-once under concurrency. Live Paystack test payment in the books: TFML 285,000 invoiced / 287,000 received, flagged.

## Slide 17
TRACK B · MONEY
Day 6
Money going out — only through the gate
COMPLETE
What was delivered
Vendor payouts and custodial landlord rent remittance, both live.
No payment moves without passing verify → performance → approve → remit.
Management and admin fees retained; the landlord receives the balance.
Remittance advice, and a safe path if a transfer's outcome is ever unknown.
THE REAL DEMONSTRATION
The gate refused every unverified, unscored or unapproved payment. Three simultaneous attempts on one payout produced exactly one payment. Fees landed in fee income and the landlord received the net. An unrecognised ₦5,000,000 liability was refused, and a transfer of uncertain outcome was held for a person rather than guessed.
The B4 payment gate: no vendor is paid until service is verified and performance clears the threshold — here 93.4 vs a 70 minimum.
Notes: Day 6 gate: verify-remittance — gate refuses every incomplete payment; 3 concurrent claims -> 1 winner; re-confirming posts once; cannot pay more than owed; unknown stays unknown. Payment-gate screenshot embedded (assets/04-payment-gate.png): Sparkle Cleaning Services, INV-3IUY9A-7f7f, 180,000, verified, performance 93.4 Excellent vs threshold 70.

## Slide 18
GOVERNANCE
Day 6.5
Permissions become an operator's switches
COMPLETE
What was delivered
Who can do what is now settings an operator toggles, not rules buried in code.
Only the OE Group operator portal can change them; each brand sees its own, read-only.
Money and audit controls are permanently locked, shown on screen with the reason.
Any drift from the board-approved baseline is badged, with one-click reset.
THE REAL DEMONSTRATION
Flipping a single permission changed what the database itself returned — switch it off and the data disappeared, switch it back and exactly what was there returned. The locked money and audit controls refused to move; a brand administrator could view but not edit their own matrix, and could not see another brand's; and every change was recorded naming both organisations. Proven by 24 checks against live logins.
Notes: Day 6.5 gate evidence from BUILD_JOURNAL.md (2026-07-27 'Day 6.5 — the permission matrix'): verify-permissions.mjs, 24 assertions — a toggle changes what the DATABASE returns (revoke -> zero rows, restore -> exactly what was there); a revoked write is refused; four locked capabilities refuse to move; an invented capability is refused; a brand admin can read but not edit their own matrix and cannot see another's; a tenant cannot edit at all; isolation and identity survive every toggle off; the trail names both orgs. Commit 74f3816 (migrations 0050-0055). NOTE: the one-glance Status board table was not updated to mark this done; verified via the build journal + commit.

## Slide 19
PORTFOLIO
Day 6.75
Properties and units can finally be enrolled
COMPLETE
What was delivered
Staff can now create and manage properties and units inside the app itself.
Units carry occupancy, bulk import, and facility-manager assignment.
Guardrails protect the service-charge split: unique unit names, positive shares.
A property or unit cannot be retired while occupants or unpaid charges remain.
THE REAL DEMONSTRATION
Attaching a facility manager to a property immediately made it visible to them, and detaching removed it again — proven against live logins, so the assignment is the access, not a label. A bulk unit import was all-or-nothing, its preview showing each unit's resulting share of the service charge as a percentage; and a property still holding live units or unpaid charges refused to be retired. Confirmed by 17 checks.
Notes: Day 6.75 gate evidence from BUILD_JOURNAL.md (2026-07-27 'Day 6.75 — properties and units become manageable'): verify-properties.mjs, 17 checks — attaching an FM to a property makes it visible and detaching removes it, asserted against live sessions; all-or-nothing bulk import with a percentage-share preview; unique unit label per property and a strictly positive apportionment factor enforced in the DB; retire refuses while obligations remain, hard delete blocked. Commit 3ed049d (migration 0056). This stage was 'missed, not deferred' — every property had previously come only from seed scripts. NOTE: not reflected in the one-glance Status board table; verified via build journal + commit.

## Slide 20
TRACK C — OEA LETTINGS
Day 7
OEA's front door opens for applicants
COMPLETE
What was delivered
Prospective tenants apply on their phone — individual or corporate, documents attached.
Explicit NDPA consent is captured; a rejected application purges automatically after 90 days.
Save-and-resume: a half-finished application can be picked up later from an emailed link.
Which documents are mandatory is now admin configuration, not code.
THE REAL DEMONSTRATION
A live audit found submission silently blocked end to end — a document check that quietly returned zero rows instead of erroring, so every uploaded file read as missing. Closed at the database layer: the gate now lives inside the submission function itself, fields that had no reason to be readable were locked down, and the resume-by-email link the form promised was made to actually work. 48 checks across three suites confirm it end to end.

## Slide 21
TRACK C — OEA LETTINGS
Day 8
Applications move through review, not a spreadsheet
COMPLETE
What was delivered
Two-tier review: a scoped FM/PM recommends, admin or finance approves — never the same person.
Individual applications need one approval; corporate need two independent approvers.
Approval automatically creates the tenant's login and allocates the unit.
Every recommend, request-info, approve and reject is recorded with its author and reason.
THE REAL DEMONSTRATION
A blocker found in review: every application arrived with no property attached, so a property-scoped reviewer's queue was correctly empty. Closed by having the applicant's own form carry the property forward. Verified live in the browser against a real applicant submission: the review queue, a live recommendation, and the system correctly refusing to let the recommender also approve their own case. 35 checks.

## Slide 22
TRACK C — OEA LETTINGS
Day 9
Leases, rent, and the roll a landlord can actually be handed
COMPLETE
What was delivered
Lease creation, term, rent and escalation — one unit can never be let twice over the same dates.
Rent billed annually in advance, the Nigerian norm, with each landlord's own fee rate honoured.
Renewal notices fire automatically at 90/60/30 days; rent demands now raise themselves too.
Rent reaches the ledger automatically, splitting the landlord's share and OE Group's fee.
THE REAL DEMONSTRATION
Every rate is snapshotted onto the transaction the moment it's collected, so a later fee change can never silently rewrite a past landlord statement. A gap closed on 3 August: rent demands used to depend on someone remembering to click “Bill rent” — with rent billed a year at a time, that is a year's income never asked for. Demands now raise themselves daily, each one exactly once. 47 checks across three suites.

## Slide 23
TRACK D — INTELLIGENCE & EXPERIENCE
Day 10
A dashboard that answers the board's question live
COMPLETE
What was delivered
A filterable analytics console for both brands: date, property, vendor, category, status, trends.
Fastest/slowest vendor, completion by category, average time-to-resolve — computed live.
CSV export and a branded PDF report always match the numbers shown on screen.
A tenant's own “Track my request” timeline, and a vendor's own pipeline-and-scorecard view.
THE REAL DEMONSTRATION
A fact nobody had written down: the system never recorded the moment a ticket resolved, so “average time-to-resolve” was uncomputable, until now — every average states on screen exactly what it measured. A partial period is no longer mistaken for a decline: three days of August against a full July used to print “−81% raised” in red — fixed before anyone saw it live. 32 checks.

## Slide 24
TRACK D — INTELLIGENCE & EXPERIENCE
Day 11
A vendor's score comes from a checklist and a clock, not a guess
COMPLETE
What was delivered
Response and completion time are measured automatically against an admin-set SLA target.
Quality and compliance come from an FM/PM checklist; satisfaction from the tenant's own rating.
Photo and video evidence on every work order, capped, private, and ticket-scoped.
A measured accessibility pass: every tinted badge and muted text fixed for contrast, both themes.
THE REAL DEMONSTRATION
No free-typed score is possible anywhere in the write path — verified live in the browser as both roles: a tenant rates a job, an FM/PM completes the checklist, and the vendor's scorecard updates immediately to the composite the AURA weights actually specify. 26 checks on the scoring alone, plus 20 more on work-order media.

## Slide 25
Roadblocks — and how they are being handled
None of these stopped the build. Each is an external dependency waiting on paperwork or access, framed as issue → impact → status.
1
Meta / Facebook business verification
Issue: Verification was held up because the information Facebook referenced in the business-registration document is inconsistent with the details submitted. Impact: OEA's WhatsApp display name and higher messaging limits stay pending. Status: Superseded, 4 Aug. Both numbers moved onto 360dialog as direct clients instead — TFML’s identity is confirmed verified via 360dialog’s own route; OEA is live under an interim display name pending the same.
2
Paystack setup
Issue: Incomplete business-registration information is blocking the Paystack account from being fully set up. Of particular interest is the latest additions of the “SCUML Certificate” and “Proof of Identity and Addresses for shareholders that own up to 51% of TFML.” requirement. Impact: Live Naira collections cannot go live until the account clears (test mode works today). Status Still open — same registration pack as Flutterwave. Live (test-mode) Paystack collections and vendor/landlord remittances already run end to end on the dev deployment while the account clears.
3
Flutterwave setup
Issue: The same incomplete registration information is blocking the Flutterwave account. Impact: Foreign-currency collections cannot go live; the system refuses them cleanly for now. Status No longer blocks the build — the segregated FX ledger, Settings → Banking and FX checkout are fully built and verified (21 checks). Adding the live key is the one remaining step.
4
OEA email-domain routing
Issue: No access to OEA's email host, so the branded sending records cannot be created. Impact: OEA cannot yet send branded email from its own domain. Status Requesting host access from OEA; sending is configured and waiting on the DNS records.
Notes: Four external-dependency roadblocks, all from the records. Meta verification is held up by inconsistent info in the referenced business-registration document (BUSINESS_VERIFICATION.md notes ~99% of rejections are detail mismatches). Paystack and Flutterwave both blocked by incomplete registration information. OEA email routing blocked by lack of access to OEA's email host. None blocked the build.

## Slide 26
ROADBLOCK #5 · DISCOVERED DURING THE BUILD
A near-miss with TFML's live business email
ISSUE
Two problems surfaced while wiring email. The master brief carried the wrong TFML domain (tfmconsultant.com, which does not exist — the real one is tfmlconsultant.com). And adding email sending to the main domain would have pushed its sender records past a strict technical limit.
IMPACT
Under TFML's existing strict mail policy, crossing that limit would have caused genuine staff email to be rejected outright — not merely spam-foldered. A routine feature could have disrupted live business email across the company.
STATUS
Resolved. The domain was corrected at source, and each brand now sends from a dedicated, isolated sub-domain that leaves the main mail records untouched. Verified live: the main records are byte-for-byte unchanged and mail still delivers under full protection.
Notes: The discovered fifth roadblock, taken from BUILD_JOURNAL.md (2026-07-25 'Email sending domain + reply routing'). The brief's TFML domain did not exist, and adding Resend to the root domain would have tipped its SPF past the 10-lookup RFC limit — under -all + DMARC p=reject that rejects genuine staff mail. Resolved by correcting the domain and sending from the notify. subdomain; verified live with root records unchanged.

## Slide 27
Where we are, and what's next
15
stages complete
of 16 on the roadmap
3
money tracks live
ledger · collect · remit
1
known money defects
1 open (SC-budget race) · vendor-score gate fixed 6 Aug.
Current stage
Five more tracks have landed since: OEA applicants can now apply, be reviewed and approved straight into a tenancy; leases, rent billing and the rent roll are live with self-raising demands and renewal notices; the interactive analytics console answers the board’s own questions live; and a vendor’s score now comes from a checklist and a clock, not a free-typed guess. The foundation and full money-path tracks remain complete and verified against the real gateway.
The immediate next step
Day 12 — Security, compliance, UAT and go-live. The production security pass, NDPA compliance pack and multi-role UAT are underway. Of Monday’s two audit findings, the vendor-score/payment-gate defect was fixed 6 Aug with a regression test; a billing-race guard on SC budgets remains open. Go-live still needs the board: DPO designation, processor DPAs, live payment keys and the go/no-go after a clean UAT.
Board Confidential · 5 August 2026
Notes: Summary: 10 of 16 roadmap stages done — the whole money path is live and verified, permissions are operator-governed, and property/unit enrolment now exists in-app. Next is Day 7 (OEA tenant application + KYC), opening the OEA lettings track (Days 7-9).